## Working route
Blackboard Group No ?? Class XYY | Project Planning |  |  |  |  | Version 1 |  |  |  |  | Version 2 (optional) |  |  |  |  | Version 3 (option) |  |  |  |  | Last Chance Submission
SMART goals ==> | Specific tasks and WBS | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING TESTING (not) DONE DONE LATE HUNG UP | Specific tasks and WBS | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING TESTING (not) DONE DONE LATE HUNG UP | Specific tasks and WBS | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING TESTING (not) DONE DONE LATE HUNG UP | Specific tasks and WBS | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING TESTING (not) DONE DONE LATE HUNG UP | Specific activities | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING TESTING (not) DONE DONE LATE HUNG UP
reference and relative due dates |  | Update E3 to your PM class date | =====> | 2023-11-17 | Friday Nov.17 |  |  | PM class date plus | 9 | days |  |  | PM class date plus | 14 | days |  |  | PM class date plus | 21 | days | Latest possible submission is last day of classes; late penalties apply at 20% per day after your Version 3 due date: | 2023-12-14
Each Team member | Your Project Mgmt notes on what each Process Group means to you when doing this project. | Share with team by uploading PM-Notes-myName.docx to Bb ## team channel's Files |  | Sunday Nov.19 | TO DO | completes their module. For specific tasks, see Final Project Overview and Project Milestones and Details | see Programming Comments and Programming Test Cases docs for acceptance criteria. See Project Overview - Appendix B for deliverables |  | see Project Milestones and Details |  | completes their module. For specific tasks, see Final Project Overview and Project Milestones and Details | see Programming Comments and Programming Test Cases docs for acceptance criteria. See Project Overview - Appendix B for deliverables |  | see Project Milestones and Details |  | completes their module. For specific tasks, see Final Project Overview and Project Milestones and Details | see Programming Comments and Programming Test Cases docs for acceptance criteria. See Project Overview - Appendix B for deliverables |  | see Project Milestones and Details
Team Meeting Agenda ==> | create MS Teams Private Channel; for Version 1, create plan with SMART goals and assign tasks | detailed tasks assigned to Team members with est. hrs., agreed upon delivery date to Teams, updated Status | 1.5 | Monday Nov.20 | TO DO | review progress, refine Plan, update DONE items with actual hours, refine estimates and delivery date/time | In MS Team Channel, select any file you would like reviewed and send a message @instructor to comment on that file. |  | Friday Nov.24 | TO DO | Team decision whether to do this version. If so, members plan to complete V2 of their module. | detailed tasks assigned to Team members with est. hrs., agreed upon delivery date/time to Teams, updated Status |  | Wednesday Nov.29 | TO DO | Team decision whether to do this version. If so, members plan to complete V3 of their module. | detailed tasks assigned to Team members with est. hrs., agreed upon delivery date/time to Teams, updated Status |  | Wednesday Dec.6 | TO DO | Submit final version of artefacts from Teams to Blackboard in a .ZIP archive. Backup Team's files. | updated all DONE items with actual hours. |  | Monday Dec.11 | TO DO
| request review from professor | Request review of this file: see Project Milestones and Details page, "Request review of a file..." |  | Tuesday Nov.21 |  | request review from professor | Request review of this file: see Project Milestones and Details page, "Request review of a file..." |  | Friday Nov.24 | TO DO | request review from professor | Request review of this file: see Project Milestones and Details page, "Request review of a file..." |  | Wednesday Nov.29 | TO DO | request review from professor | Request review of this file: see Project Milestones and Details page, "Request review of a file..." |  | Wednesday Dec.6 | TO DO
[John De Appolonia] Fundamentals | After reviewing the assignment, we assigned tasks to each member evenly. | We each created and reviewed each members SMART goal plans to ensure we are all on the right path to completing our tasks. | 1hr 1.5hr | Monday Nov.20 | DONE | Create the code as displayed, ensure proper functionality, write comments and unit tests. | Program works as intended, unit test sheet filled out and completed, program comments are clear and concise. | 2hr 3hr | Saturday Nov.25 | DONE | Implement the new version two piece of code and record unit tests and create comments. | The sucessful completition of the new code and passing of all unit tests | 3hr | Thursday Nov.30 | DONE | Add final v3 code, comment it, run tests and upload all files | All test results have passed, git has a save of the lastest commits, and everything is uploaded on MS teams and github. | 1hr | Thursday Dec.7 | DONE |  |  |  | Tuesday Dec.12
[Ashton Miguelle Mendoza] Manipulations | Review each other's PM notes on process Teams. Agree on how project will be done. Decide which module to do & choose Team Leader | Read all the files uploaded in blackboards and made a to do litst that is needed to complete my assigned tasks. All communicated through Microsoft Teams. | 2hr - 2.5hr | Monday Nov.20 | Done | Copy, Build and create the code given. Write comments and runs multple test | The programs works for the most parts but when testing extreme cases, it would be recommended to have error handlers and clear input buffers | 2hrs - 3hrs | Saturday Nov.25 | DONE | Implement the code in your chosen IDE. Compile it. Go through proper testing procedures and record it in an excel sheet. | Completed the implemtation of version 2 along with | 2hrs - 3hrs | Thursday Nov.30 | DONE | add the final version of the code. Do final testing with every code block. Upload in git. Compile all testing methods | Multiple test have been done and for the most part they passed bu when taken to extreme cases the code fails. I finalized all my testing to one file, uploaded to git and msteams all my requirements | 2hrs - 3hrs | Thursday Dec.7 | DONE |  |  |  | Tuesday Dec.12
[Kittikhun Komonpis] Tokenizing | Review each other's PM notes on process Teams. Agree on how project will be done. Decide which module to do & choose Team Leader | Select module to work with and read all related documents. | 1.5 hr / 2.5 hr | Monday Nov.20 | DONE | Write and comment code from course's provided. And test program. | Program works as it should be. And all module test result have passed. | 2 hr / 3 hr | Saturday Nov.25 | DONE | Add new block in code and update git version | Test results of new code block have passed, and the sorce code have backup in git. | 2 hr / 3 hr | Thursday Nov.30 | DONE | Add sentence tokenizing code block in program and update git version | Test results all version have passed, and the sorce code have backup in git. | 1 hr / 0.75 hr | Thursday Dec.7 | DONE |  |  |  | Tuesday Dec.12
[Lena Park] Conversions Team Leader | We allocate each section. We also created teams channel and set up for a meeting on 30th November at 9am. | Each part was selected by member's own choice and agreed that we must upload our work until deadline. | 2 hours¦ 3hours | Tuesday Nov.21 | DONE | Created file following instruction, tested code how converting works in the code, examined the result. | The code worked as I intended | 2.5h¦3h | Sunday Nov.26 | DONE | REPLACE THIS with your action items and work breakdown structure for this Version | The new code was built successfully and passed unit tests. I added comments on non-pass unit tests. | 2 hr ¦ 3.5hr | Friday Dec.1 | DONE | I gathered all the files that members submitted in Teams and compiled them | It expected as I expected and uploaded in Teams and github. | 4hr¦5hr | Friday Dec.8 | DONE |  |  |  | Wednesday Dec.13
|  |  |  | milestone upload to Blackboard |  |  |  |  | milestone upload to Blackboard |  |  |  |  | milestone upload to Blackboard |  |  |  |  | DUE DATE upload to Blackboard |  |  |  |  | ABSOLUTE DEADLINE
[6 empty] | "Work on [module name]" is not specific. There are tasks with a critical path. WBS? Filenames to be uploaded to your team's Files area. | What is the team's criteria for acceptance of development (files on developer's PC) when promoted to integration (Files in team's channel) What file names? What is definition of done / good enough? Who decides that? Project Overview and Programming Comments¦Testing docs have this information to be quoted or referenced. Requests for professor's review come after the team has accepted the work. | [11 empty] | submissions after this date subject to extra time charge of 20% per day |  |  |  |  | no submissions accepted after this date
Note on A1: Update ?? to your Blackboard group number and XYY to your CPR101XYY class code. Then press TAB to next set up item in E3.
Note on A2: Use SMART goals to achieve the Triple Constraint of Cost/Resource vs Time/Schedule vs Scope/Quality.
Note on B2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on C2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on D2: How many hours will the task take?
Note on E2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on F2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: work in progress: an objective or task according to a Time based target – hours of effort will be completed by a due date & time TESTING: work promoted by team member after Doing to other team members for Testing/Measurement. DONE: an objective or task Tested/Measured as completed. Only Team leader can change status to DONE (or back to DOING for rework or HUNG UP for problem resolution) HUNG UP: no longer doing something because it became unRealistic. Tell the team right away. E.g. hours required will not be completed by the due date-time; specific objectives were found to be too vague when Doing; no metrics were applied to measure doneness.
Note on G2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on H2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on I2: How many hours will the task take?
Note on J2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on K2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: work in progress: an objective or task according to a Time based target – hours of effort will be completed by a due date & time TESTING: work promoted by team member after Doing to other team members for Testing/Measurement. DONE: an objective or task Tested/Measured as completed. Only Team leader can change status to DONE (or back to DOING for rework or HUNG UP for problem resolution) HUNG UP: no longer doing something because it became unRealistic. Tell the team right away. E.g. hours required will not be completed by the due date-time; specific objectives were found to be too vague when Doing; no metrics were applied to measure doneness.
Note on L2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on M2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on N2: How many hours will the task take?
Note on O2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on P2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: work in progress: an objective or task according to a Time based target – hours of effort will be completed by a due date & time TESTING: work promoted by team member after Doing to other team members for Testing/Measurement. DONE: an objective or task Tested/Measured as completed. Only Team leader can change status to DONE (or back to DOING for rework or HUNG UP for problem resolution) HUNG UP: no longer doing something because it became unRealistic. Tell the team right away. E.g. hours required will not be completed by the due date-time; specific objectives were found to be too vague when Doing; no metrics were applied to measure doneness.
Note on Q2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on R2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on S2: How many hours will the task take?
Note on T2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on U2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: work in progress: an objective or task according to a Time based target – hours of effort will be completed by a due date & time TESTING: work promoted by team member after Doing to other team members for Testing/Measurement. DONE: an objective or task Tested/Measured as completed. Only Team leader can change status to DONE (or back to DOING for rework or HUNG UP for problem resolution) HUNG UP: no longer doing something because it became unRealistic. Tell the team right away. E.g. hours required will not be completed by the due date-time; specific objectives were found to be too vague when Doing; no metrics were applied to measure doneness.
Note on V2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on W2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on X2: How many hours will the task take?
Note on Y2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on Z2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: work in progress: an objective or task according to a Time based target – hours of effort will be completed by a due date & time TESTING: work promoted by team member after Doing to other team members for Testing/Measurement. DONE: an objective or task Tested/Measured as completed. Only Team leader can change status to DONE (or back to DOING for rework or HUNG UP for problem resolution) HUNG UP: no longer doing something because it became unRealistic. Tell the team right away. E.g. hours required will not be completed by the due date-time; specific objectives were found to be too vague when Doing; no metrics were applied to measure doneness.
Note on E3: Change this to the date of your Project Management class and the worksheet will calculate all milestone dates.